## Slide 1
Northbank Group kickoff
Wednesday 18 November 2026, 10:00 New York time (17:00 Harare)
Cedarline Partners, prepared by the executive assistant for Jordan Hale
Notes: Open with the purpose: agree goals, scope and the first four weeks, and collect access. Fictional company and client.

## Slide 2: Four weeks, three goals, one owner for every action
1
Clear scope
Agree what is in the four week plan and what waits
2
Access in place
Accounts and files requested on day one, chased on day three
3
Rhythm set
Friday check in and a weekly update that fits one page
Notes: Keep this slide to two minutes. Priya speaks to goals, Jordan to scope.

## Slide 3: Agenda, with both time zones
New York (Harare) | Item | Lead
10:00 (17:00) | Welcome and introductions | Jordan Hale
10:10 (17:10) | Goals and success measures | Priya Nair
10:35 (17:35) | Scope and timeline | Jordan Hale
11:00 (18:00) | Access and tools checklist | Tom Eze
11:20 (18:20) | Risks and questions | All
11:40 (18:40) | Next steps and owners | Assistant reads back
Notes: New York is UTC-5 from 1 November, so Harare is seven hours ahead on this date.

## Slide 4: Three risks and what happens about each
Access arrives late
List goes out on day one, chase on day three
Owner: Assistant
Scope grows on the call
New asks go on a parking list and are decided after the call
Owner: Jordan Hale
Time zone slip
Every follow up confirms the time in both zones in writing
Owner: Assistant

## Slide 5
After the call
Minutes and action list to Jordan within one hour
Each action has one owner and one date
Follow up email waits in drafts until Jordan approves
Weekly update lands every Friday, one page
Notes: Close by reading back the actions with owners and dates.